## Sprint 1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2024-11-05
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | NLP Methoden&NLTK recherchieren | 4 | 5 | 1 | yes |  | Zeliha Vural
2 | NLP, NLTK, Python Libs ansehen | 4 | 4 | 0 | yes |  | Luis Böhler
3 | NLP & RAG Frameworks angeschaut | 3 | 4 | 1 | yes |  | Kevin Alexander
4 | Frameworks/API's researchen (spaCy, Transformers, Haystack) | 5 | 4 | -1 | yes |  | Sonja Lechner & Niklas Brandtner (Group Research)
5 | Nachforschungen für nützliche Technologien (Glob, Whoosh, Apache Tika etc..) | 3 | 4 | 1 | yes |  | Sonja Lechner & Niklas Brandtner (Group Research)
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint 2
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2024-11-19
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Github Roadmap updaten | 6 | 6 | 0 | yes
2 | User Stories hinzufügen | 10 | 8 | -2 | yes
3 | Fortschrittsbericht erstellen | 5 | 4 | -1 | yes
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -3 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint 3
Sprint Review Protocol
Sprint No: |  | 3
Date & Time
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Test NLP Examples & Research similar Projects | 10 | 8 | -2 | yes |  | Niklas Brandtner & Sonja Lechner
2 | SpaCy Course | 10 | 9 | -1 | yes |  | Luis Böhler
3 | Dokumente sammeln& Python lernen | 8 | 8 | 0 | yes |  | Zeliha Vural
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -3 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint 4
Sprint Review Protocol
Sprint No: |  | 4
Date & Time
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 |  |  |  | 0
2 |  |  |  | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint 5
Sprint Review Protocol
Sprint No: |  | 5
Date & Time
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 |  |  |  | 0
2 |  |  |  | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint 6
Sprint Review Protocol
Sprint No: |  | 6
Date & Time
Group Number |  | 4
Participant 1 |  | Alexander Kevin
Participant 2 |  | Böhler Luis
Participant 3 |  | Brandtner Niklas
Participant 4 |  | Lechner Sonja
Participant 5 |  | Vural Zeliha
Mentor |  | Knapp Bernhard
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 |  |  |  | 0
2 |  |  |  | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol